## Overview
Planning – site survey

Conduct site survey started?	In process			Progress					Responsibility
Conduct site survey	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Network points	Yes			66.67%	33.33%	BTG	RIL (Vivian)	RIL Branch manager	Other	55.56%	22.22%	11.11%	11.11%
CCTV camera locations	Yes					RIL (Vivian)
Data cabinet(s)	No					RIL (Vivian)
UPS system(s)	Yes					RIL (Vivian)
Collaborate with Branch manager on network and CCTV requirements	Yes					RIL (Vivian)
Number & location of data points and CCTV camera locations established	No					RIL Branch manager
Network cabling	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Develop detailed network cabling plan based on site survey or get this from building contractor?	Yes			100.00%	0.00%	RIL (Vivian)	RIL Branch manager	Other	BTG	25.00%	25.00%	25.00%	25.00%
Cambium switches	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Assess requirement to determine type and number of switches needed	Yes			33.33%	66.67%					0.00%	0.00%	0.00%	0.00%
Get quote from BTG for switch(es)	No
Review quote & get approval	No
Data cabinets	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Assess requirement for data cabinet(s)				0.00%	0.00%	BTG				0.00%	0.00%	100.00%	0.00%
Data cabinet location(s)
Contact PB tech for quote
Review quote and seek approval
Routers	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
BTG to provide and configure router(s)				0.00%	0.00%	RIL (Vivian)		RIL (Vivian)		100.00%	0.00%	0.00%	0.00%
UPS system(s)	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Assess the power requirements of routers and switches to determine the appropriate capacity for UPS systems.				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
Obtain a comprehensive quotation from BTG & PB Tech for the UPS systems.
Review the quotation and seek necessary approvals.
WAN services	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Collaborate with branch manager regarding site requirements for land line number				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
Internet connectivity (300 / 300 or 500 / 500) as available
BTG Service Delivery Agreement (SDA)	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
SDA to be signed by Graeme Gellatly or Jason Crawford				0.00%	0.00%	BTG				0.00%	0.00%	100.00%	0.00%
Procurement	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Issue purchase orders for the routers based on approved quotations if needed				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
Issue purchase orders for the switches based on approved quotations if needed
Issue purchase orders for the UPS systems based on approved quotations if needed
Fiber	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Is there Fiber conduit for Fiber run				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
Has Fiber been installed from curb to the building
Has ONT & Fiber been installed on site in the data / server room
Installation and Configuration:	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
BTG or RIL to deploy qualified technicians to install and configure routers				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
BTG or RIL to deploy qualified technicians to install and configure switches
BTG or RIL to deploy qualified technicians to install and configure UPS systems
BTG or RIL to deploy qualified technicians to install and configure CCTV system (if included)
Deploy technician to install network cabling
Cables terminated in data / server room behind data cabinet(s)
Ensure proper connectivity and integration with the existing network
Testing	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Conduct thorough functional testing of the entire ITC infrastructure.				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
Verify UPS functionality
Verify CCTV camera feeds (if deployed)
Verify network connectivity
Documentation	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Create as-built documentation that includes network diagrams, cabinet layouts, and equipment configurations.				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
Document any deviations from the original plan.
Training	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Provide training sessions for end-users on the proper use of the new ITC infrastructure.				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
Offer support and address any user concerns.
User equipment	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Collaborate with Branch manager on user equipment requirement				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
Get quote from BTG for telephones
Get BTG to create 3CX accounts
BTG to send devices to branch
Get quote from Dell for laptops
Get quote from PB Tech for screen(s) keyboard and mouse kits – delivery directly to branch
Provision of laptops	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Setup with admin user and install with powershell script				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
Login to Teamviewer on laptop and add to account
Open UltraVNC and start service
Configure UltraVNC passwords
Courier laptop to user/branch when done
Handover	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Officially hand over the completed ITC infrastructure to the branch manager.				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
Provide documentation, contact information for support, and ensure user satisfaction.
Post-Implementation Review:	Response	Timestamp	Comments	Yes	No	Responsibility				RIL (Vivian)	RIL Branch manager	BTG	Other
Conduct a post-implementation review to identify lessons learned and areas for improvement.				0.00%	0.00%					0.00%	0.00%	0.00%	0.00%
Document recommendations for future projects

## Graphs
Design network plan or get from building contractor					Design network progress
Conduct site survey responsibilities Conduct survey % yes vs No